## Overview
Stretch Assist
Autonomous object retrieval and delivery through an accessible command interface
Course | Robotics and Cyber-Physical Systems
Institution | School of Sciences and Engineering, Tecnologico de Monterrey
Platform | Stretch MuJoCo Digital Twin (stretch_mujoco_digital_twin)
Team | Gustavo (technical lead, 80 h) and Luis (interface and evidence, 30 h)
Total effort | 110 h
Document version | 1.1
Sheets in this workbook
Functional Requirements | What the system must do (RF-01 to RF-12).
Non-Functional Requirements | Quality attributes and constraints (RNF-01 to RNF-09).
Task Breakdown | Work packages with owner, hours and the requirements each one covers.
Hours Summary | Hours per person, computed from the task breakdown.

## Target Objects
Target Objects
Each object has an ArUco marker sticker attached. The robot identifies the object from the marker ID.
ArUco ID | Object | Description | In Scope
0 | Medicine box | Small cardboard box representing a medication container. | Yes
1 | Glass | Cylindrical cup for drinking. | Yes
2 | Tissue | Flat, lightweight cloth or paper tissue. | Yes

## Functional Requirements
Functional Requirements
ID | Requirement | Priority | Owner | Task | Justification
RF-01 | The system must let the user select the target object through an accessible command (voice or large button). | High | Luis | T7 | It is the entry point that delivers the accessibility value. A user with reduced mobility cannot use a keyboard or gamepad.
RF-02 | The system must detect the target object by identifying its ArUco marker (ID 0 = medicine box, ID 1 = glass, ID 2 = tissue) in the RGB frame of the head camera using cv2.aruco. | High | Gustavo | T1 | ArUco markers are robust under the simulator lighting conditions and transfer directly to the physical robot without recalibration.
RF-03 | The system must estimate the 3D position of the detected object by combining the ArUco marker centroid, the pixel depth from the depth camera, and the camera intrinsics. | High | Gustavo | T1 | Without a 3D position the robot cannot approach or grasp. The toolkit already exposes the depth frame and camera intrinsics.
RF-04 | The robot must run an autonomous search (rotating the base and head) until it locates the object when it is outside the initial field of view. | High | Gustavo | T2 | The object will not always be in front of the robot, so the search makes the system genuinely autonomous.
RF-05 | The robot must approach the object autonomously using base velocity control. | High | Gustavo | T2 | The object is usually outside the arm reach, so the mobile base has to reposition.
RF-06 | The robot must perform fine alignment of the end effector through visual servoing with the wrist camera. | High | Gustavo | T3 | Base approach is not precise enough to grasp, so the wrist camera corrects the residual error.
RF-07 | The robot must close the gripper on the object and verify that the grasp succeeded. | High | Gustavo | T3 | Grasping without verification produces false successes, so verification enables retries (see RNF-05).
RF-08 | The robot must return to the user position and release or hand over the object. | High | Gustavo | T4 | This closes the assistance cycle. The goal is to deliver the object, not only to pick it up.
RF-09 | The operator must be able to take manual control (keyboard or gamepad) at any time, with priority over autonomous control. | High | Gustavo | T4 | Safety requirement for assistive applications. The toolkit already offers merge_proportional, where the human wins.
RF-10 | The system must give feedback about the robot state to the user (visual or audio: searching, grasping, delivering). | Medium | Luis | T8 | An assisted user needs to know what is happening, which improves trust and usability.
RF-11 | The full behavior must be orchestrated through a state machine (SEARCH, APPROACH, ALIGN, GRASP, RETURN, RELEASE). | High | Gustavo | T4 | It structures the system, eases debugging and allows error transitions. The toolkit includes StateController.
RF-12 | The system must run without code changes both in simulation and on the physical robot. | Medium | Gustavo | T5 | This is the explicit goal of being easy to apply to the physical robot, achieved by using only the stretch_toolkit API.

## Non-Functional Requirements
Non-Functional Requirements
ID | Requirement | Category | Owner | Verification criterion
RNF-01 | Sim-to-real portability: the same script runs on both backends. | Portability | Gustavo | Code review confirms that only the stretch_toolkit API is used, with no MuJoCo specific calls in the control logic.
RNF-02 | Safety: operator control always has priority and a safe stop exists. | Safety | Gustavo | During an autonomous operation, a manual input interrupts and takes over the robot.
RNF-03 | Performance: the control loop runs at about 30 Hz with minimal perceptible latency. | Performance | Gustavo | Measure the real loop frequency and disable unused cameras if performance drops.
RNF-04 | Usability and accessibility: the interface is operable by a person with reduced mobility. | Usability | Luis | Scenario test: complete a request using only voice or a single large button.
RNF-05 | Robustness: the system handles object not found and grasp failure with retries or a controlled abort. | Reliability | Gustavo | Hide the object and force a failed grasp, then confirm the system does not hang.
RNF-06 | Zero cost and no extra hardware: everything runs in the simulator with the laptop microphone. | Constraint | Luis | The full project runs without any purchase.
RNF-07 | Maintainability: modular code with parameters adjustable through a configuration file (JSON hot reload). | Maintainability | Gustavo | Changing a gain or a speed value in JSON takes effect without restarting.
RNF-08 | Reproducibility: the project installs and runs with uv run following the README on Windows, macOS and Linux. | Reproducibility | Gustavo | A third party clones the repo and runs the demo by following the document.
RNF-09 | Success metric: successful grasp and delivery rate of at least 70 percent over N attempts. | Quality | Luis | Log of N runs counting successes and failures.

## Task Breakdown
Task Breakdown (Work Packages)
Task | Description | Owner | Hours | Requirements covered | Deliverable
T0 | Environment setup, repo study (teleop_demo.py, visual_servoing.py, stretch_toolkit) and a short literature review on assistive robotics. | Gustavo | 8 | RNF-08 | Working environment and architecture notes.
T1 | Perception module: ArUco marker detection for the three target objects (IDs 0-2) and 3D position estimation (marker centroid, depth, and camera intrinsics). | Gustavo | 14 | RF-02, RF-03 | perception.py with detect_object(frame, depth_frame) returning object name, ArUco ID, and 3D position.
T2 | Autonomous search and approach: rotate base and head to locate the object and use base velocity control to get closer. | Gustavo | 16 | RF-04, RF-05, RNF-03 | search() and approach() behaviors.
T3 | Grasp pipeline: visual servoing alignment with the wrist camera, gripper close and grasp verification. | Gustavo | 16 | RF-06, RF-07 | grasp() behavior with verification.
T4 | State machine integration (SEARCH to RELEASE) plus manual override and error transitions. | Gustavo | 12 | RF-08, RF-09, RF-11, RNF-02, RNF-05 | state_machine.py running end to end.
T5 | Sim-to-real validation, gain tuning through JSON and a test matrix. | Gustavo | 8 | RF-12, RNF-01, RNF-07 | Compatibility report and tuned config.
T6 | Technical documentation and the technical section of the final report. | Gustavo | 6 | Deliverables | Technical section of the report.
T7 | Accessible command interface: offline voice recognition (Vosk or speech_recognition) or a large button GUI that emits the target object. | Luis | 12 | RF-01, RNF-04 | accessible_ui.py.
T8 | State feedback to the user plus accessibility design and use scenarios with personas. | Luis | 6 | RF-10, RNF-04 | Feedback module and scenarios document.
T9 | Testing and data collection: run N trials, log success rate, failure cases and override evidence. | Luis | 6 | RNF-06, RNF-09 | Results table (successes and failures).
T10 | Evidence production: demonstration video, screenshots (RoboCasa and result) and report sections. | Luis | 6 | Deliverables | Video, screenshots and report sections.
TOTAL

## Hours Summary
Hours Summary
Person | Role | Hours
Gustavo | Technical lead (perception, navigation, grasping, integration)
Luis | Interface and evidence (accessible UI, feedback, testing, report)
TOTAL